## Template
Revspire ¦ Mutual action plan template
Fill in the header first, then adjust the milestones to your sales process. Keep owners as named people, not teams. The "Done when" column is pre-filled with suggested exit criteria you can edit.
Free template from https://www.revspire.io/resources/templates/mutual-action-plan-template (last updated 2026-10-15)
Plan header
Field | What to write | Your entry
Buyer / seller | [Buyer company] and [seller company]
Shared goal | [The business outcome the buyer wants, in their words]
Success criteria | [How the buyer will judge the evaluation a success]
Compelling event and target date | [Why this must happen by when, e.g. renewal or launch] / [date]
Buyer lead / seller lead | [Champion name and title] / [account executive name]
Last updated | [Date and who updated it]
Plan milestones
Phase | Milestone | Buyer owner | Seller owner | Target date | Status | Done when
1. Align | Problem, goals and success criteria agreed | [Name] | [Name] | [Date] | Not started | Buyer confirms the summary in writing
1. Align | Buying group identified | [Name] | [Name] | [Date] | Not started | Every role on the stakeholder map has a name or a plan to find one
1. Align | Mutual action plan reviewed together | [Name] | [Name] | [Date] | Not started | Buyer has edited and accepted the plan
2. Evaluate | Tailored demo or workshop | [Name] | [Name] | [Date] | Not started | Evaluators confirm their use cases were covered
2. Evaluate | Technical validation or pilot | [Name] | [Name] | [Date] | Not started | Agreed pilot criteria met, or gaps documented
2. Evaluate | Business case drafted with the champion | [Name] | [Name] | [Date] | Not started | Champion can present it without the seller
3. Validate | Security and IT review | [Name] | [Name] | [Date] | Not started | Questionnaire answered and reviewer signs off
3. Validate | Reference conversation | [Name] | [Name] | [Date] | Not started | Buyer has spoken to a comparable customer
3. Validate | Executive sponsor meeting | [Name] | [Name] | [Date] | Not started | Economic buyer confirms priority and budget
4. Decide | Commercial proposal | [Name] | [Name] | [Date] | Not started | Proposal accepted or redlined
4. Decide | Procurement and vendor onboarding | [Name] | [Name] | [Date] | Not started | Vendor set up in the buyer's systems
4. Decide | Legal review of contract and data terms | [Name] | [Name] | [Date] | Not started | Final terms agreed by both legal teams
4. Decide | Signature | [Name] | [Name] | [Date] | Not started | Contract signed by the authorised signer
5. Launch | Kickoff and onboarding plan | [Name] | [Name] | [Date] | Not started | Implementation owners and dates agreed
5. Launch | First value review | [Name] | [Name] | [Date] | Not started | Buyer confirms progress against the shared goal

## Example (fictional)
Revspire ¦ Mutual action plan template
Example: fictional company. Ferncastle Analytics (seller) is helping Marlow & Finch Logistics (buyer) replace spreadsheet-based sales forecasting before the buyer's new fiscal year.
Free template from https://www.revspire.io/resources/templates/mutual-action-plan-template (last updated 2026-10-15)
Plan header
Field | Example entry
Shared goal | Run the regional forecast call from one live view instead of five spreadsheets.
Success criteria | Two regional managers run a forecast call in the pilot without help from sales operations.
Compelling event | New fiscal year planning starts in week 12; the tool must be live before then.
Buyer lead / seller lead | Dana Okafor, Director of Revenue Operations / Sam Whitley, Account Executive
Plan milestones (status at week 5)
Phase | Milestone | Buyer owner | Seller owner | Target date | Status | Done when
1. Align | Goals and success criteria agreed | Dana Okafor | Sam Whitley | Week 1 | Done | Dana confirmed the recap by email
1. Align | Buying group identified | Dana Okafor | Sam Whitley | Week 2 | Done | Stakeholder map shared in the deal room
2. Evaluate | Pilot with two regions | Luis Moreno, Regional Sales Manager | Priya Nair, Solutions Engineer | Weeks 3-5 | In progress | Two forecast calls run in Ferncastle
2. Evaluate | Business case with the champion | Dana Okafor | Sam Whitley | Week 6 | Not started | Dana presents it to the CFO
3. Validate | Security review | Grace Lindqvist, IT Security Manager | Priya Nair | Week 6 | At risk | Questionnaire signed off (waiting on SSO details)
3. Validate | CFO meeting | Martin Hale, CFO | Ferncastle VP Sales | Week 7 | Not started | CFO confirms budget for next fiscal year
4. Decide | Procurement and legal | Aisha Bello, Procurement Lead | Sam Whitley | Weeks 8-9 | Not started | Terms agreed and vendor onboarded
4. Decide | Signature | Martin Hale | Sam Whitley | Week 10 | Not started | Contract signed
5. Launch | Kickoff and rollout | Dana Okafor | Ferncastle onboarding lead | Week 11 | Not started | All regions trained before planning starts
Example: fictional company. Ferncastle Analytics, Harborview Metrics, Marlow & Finch Logistics and every person named in this example are invented for illustration. Any resemblance to real companies or people is coincidental.

## How to use
Revspire ¦ Mutual action plan template
A mutual action plan template is a shared timeline that a seller and a buyer agree on together. It lists every step from discovery to signature and go-live, who owns each step on both sides, the target date and what "done" means. Use the free table below, or download the Excel or Word version with no form to fill in.
Free template from https://www.revspire.io/resources/templates/mutual-action-plan-template (last updated 2026-10-15)
1. Draft it before you propose it | Arrive at the post-discovery call with a draft based on what the buyer told you. A blank template asks the buyer to do your job; a draft gives them something to correct.
2. Work backward from the buyer's date | Start with the compelling event and the go-live date, then place signature, legal, procurement and security review before it. If the dates do not fit, say so now rather than in week nine.
3. Name a buyer owner for every buyer step | Security, procurement and legal steps need a named person on the buyer's side. A milestone with no buyer owner is a risk you should raise with your champion.
4. Define "done" for each milestone | Write the exit criteria in plain language, such as "questionnaire signed off" rather than "security". It stops a milestone from being marked complete when it is only started.
5. Agree it live and let the buyer edit | Walk through the plan on a call, invite changes and confirm it in writing. A plan the buyer has changed is a plan the buyer believes in.
6. Keep one shared version and inspect it | Store the plan where both sides can see the latest version, update it after every meeting, and review slipped buyer milestones in your deal and forecast reviews.
Common mistakes
A seller plan with a mutual label | If only the seller has tasks, the buyer has not committed to anything. Every phase needs buyer-owned steps.
Introducing it too early | Before the buyer agrees there is a problem worth solving, a plan to close feels like pressure. Earn it in discovery first.
Stopping at signature | Buyers care about go-live and results, not your quarter. Ending the plan at first value makes it about their outcome.
Turning it into a project plan | Fifty rows of tasks will not be read. Keep the plan to the milestones that move the decision, roughly one screen.
Hiding legal and procurement until late | Contract, data-protection and vendor-onboarding steps often take longer than the evaluation. Put them on the plan from the first draft.
Emailing static copies | Attachments create competing versions. Keep one live plan in a shared space and link to it.