## Template
Revspire ¦ Sales enablement plan template
Five blocks. The plan on a page comes first and should fit on one screen; the scoring, roadmap, OKRs and review cadence make it defensible. Fill them in order, because each block uses decisions made in the one before.
Free template from https://www.revspire.io/resources/templates/sales-enablement-plan-template (last updated 2026-10-26)
The plan on a page
Field | What to write | Your entry
Planning period | The year or the four quarters this plan covers, and the date of the first quarterly review.
Revenue goals served | The two or three company targets this plan supports, copied from the revenue plan rather than reworded.
Audiences in scope | Each selling role, its current headcount and the hires expected this year.
Top three outcomes | The changes in seller behaviour or results that would make this year a success, each one measurable.
Budget and headcount | The enablement budget and team size the plan assumes. If either changes, the roadmap changes.
Executive sponsor | The leader who agreed the outcomes and will hear the quarterly reviews.
Not doing this year | The requests deliberately left out, with the reason, so they are declined once instead of every week.
Initiatives scored before they are scheduled
Initiative | Revenue goal it serves | Audience | Behaviour change expected | Effort (S/M/L) | Rank
[Programme or project] | [Goal from the plan on a page] | [Role and headcount] | [What sellers will do differently] | [S, M or L] | [1 to n]
[Programme or project] | [Goal] | [Role] | [Behaviour change] | [S, M or L] | [Rank]
[Programme or project] | [Goal] | [Role] | [Behaviour change] | [S, M or L] | [Rank]
Quarterly roadmap
Quarter | Programme | Audience | Owner | Launch date | How we will know it landed
Q1 | [Ranked initiative] | [Role] | [Name] | [Date] | [Leading indicator, measured 30 days after launch]
Q2 | [Ranked initiative] | [Role] | [Name] | [Date] | [Leading indicator]
Q3 | [Ranked initiative] | [Role] | [Name] | [Date] | [Leading indicator]
Q4 | [Ranked initiative, or capacity held back for launches nobody has announced yet] | [Role] | [Name] | [Date] | [Leading indicator]
Objectives and key results
Objective | Key result | Baseline today | Target and date | Owner
[Outcome 1 from the plan on a page] | [Measurable result] | [Current value] | [Target, date] | [Name]
[Outcome 2] | [Measurable result] | [Current value] | [Target, date] | [Name]
[Outcome 3] | [Measurable result] | [Current value] | [Target, date] | [Name]
Review cadence
Rhythm | Meeting | Standing output
Monthly | Roadmap check with the enablement team | Programmes on track, at risk or slipped, with one line on why
Quarterly | Sponsor review | Key results against target, and any change to the next quarter's roadmap
Year end | Plan retrospective | Which outcomes moved, which programmes earned a second year, and what next year's plan inherits

## Example (fictional)
Revspire ¦ Sales enablement plan template
Example: fictional company. Harborview Metrics sells revenue analytics software through 85 sellers: 30 SDRs, 45 account executives and 10 account managers. It plans to hire 20 more account executives next year and to launch a second product mid-year. Tomasz Byrne runs enablement with one colleague. This is the plan he agreed with the CRO in November.
Free template from https://www.revspire.io/resources/templates/sales-enablement-plan-template (last updated 2026-10-26)
Harborview Metrics: the plan on a page
Field | What was written
Planning period | January to December, first quarterly review in the second week of April.
Revenue goals served | Grow new business bookings with a larger AE team; attach the second product to existing accounts from Q3.
Audiences in scope | 45 AEs plus 20 hires, 30 SDRs, 10 account managers. Partners are out of scope this year.
Top three outcomes | New AEs reach their first closed deal faster; every AE can run a credible discovery call on the second product by launch; reps find approved content without asking a colleague.
Budget and headcount | Two people and the current tool budget. A third hire is requested for Q3 and is not assumed.
Executive sponsor | The CRO, monthly for thirty minutes, quarterly review in writing.
Not doing this year | A full SDR certification rebuild (current one works well enough); a partner portal (no partner programme yet); an internal podcast (asked for twice, no outcome attached).
The roadmap after ranking
Quarter | Programme | Owner | How it will be judged
Q1 | Rebuilt AE onboarding with certification gates, ready for the first hiring class | Tomasz | Share of new AEs passing the discovery certification by day 45
Q2 | Content library clean-up: retire stale decks, tag the rest by stage and persona | Colleague | Searches that end in an opened, approved asset
Q3 | Second-product launch kit: pitch, discovery guide, role-play scenarios, battlecard | Tomasz with product marketing | Share of AEs certified on the new discovery call before launch week
Q4 | Half the quarter held back for whatever the launch teaches; coaching rhythm for account managers | Both | Account managers with an active coaching record
Example: fictional company. Ferncastle Analytics, Harborview Metrics, Marlow & Finch Logistics and every person named in this example are invented for illustration. Any resemblance to real companies or people is coincidental.

## How to use
Revspire ¦ Sales enablement plan template
A sales enablement plan template is a one-year plan for the enablement function: the revenue goals it serves, the few outcomes it commits to, the programmes scored and ranked before they are scheduled, a quarterly roadmap with owners and launch dates, and the OKRs and review rhythm that show whether the plan worked.
Free template from https://www.revspire.io/resources/templates/sales-enablement-plan-template (last updated 2026-10-26)
1. Start from the revenue plan, not the request list | Copy the company's targets into the plan on a page before looking at a single request. Every initiative will be scored against those goals, so they have to be fixed first.
2. Write outcomes as changes in seller behaviour | "Launch a new onboarding programme" is an activity. "New AEs run a certified discovery call by day 45" is an outcome. Three outcomes like that are enough for a year.
3. Score every initiative before any of them gets a date | List everything that has been asked for, score each against the goals, audience and effort, then rank. The roadmap is filled from the top of the ranking down, which makes the line below it a decision rather than an accident.
4. Leave room in the second half of the year | Launches, reorganisations and new hires arrive that nobody planned for. A roadmap with every quarter full has no answer when they do. Holding part of Q3 or Q4 open is part of the plan, not a gap in it.
5. Put a baseline next to every key result | A target without a starting point cannot be judged at year end. If the baseline is unknown, the first key result is to measure it, and the date for that goes on the roadmap.
6. Write the "not doing" list and share it | Requests that were declined with a reason stay declined. Requests that were simply left off come back every month. Agree the list with the sponsor and send it to the people who asked.
Common mistakes
A roadmap with twelve programmes for a team of two | Every programme needs building, launching and reinforcing. Plans that ignore the reinforcing half launch everything and land nothing. Fewer programmes, carried through, beat a full calendar.
Measuring sessions instead of change | Courses completed and assets published describe effort. Key results should describe what sellers do differently or what moved in the pipeline, measured against a baseline.
A plan written without the sponsor | If the CRO first sees the plan in January, its outcomes are enablement's wish list. Agreeing the three outcomes with the sponsor before the roadmap is built is what makes them commitments.
No link from programmes to revenue goals | An initiative that cannot name the goal it serves is the first one cut when budgets tighten. The scoring block makes the link explicit before anything is scheduled.
Never revisiting the plan | A plan that is only read at year end describes the year that was expected, not the one that happened. The quarterly review is where the roadmap is allowed to change, with a reason written down.
Confusing the plan with the charter | The plan changes every year; the charter should not. Teams that rewrite their remit in every annual plan never build a stable function, and their neighbours never learn what to expect from them.