## Template
Revspire ¦ Sales onboarding plan template
Fill in the header first: the definition of "ramped" and the certifications decide when the plan ends. Due dates are written as days from the start date. Replace bracketed numbers with your own, and keep an owner on every row.
Free template from https://www.revspire.io/resources/templates/sales-onboarding-plan-template (last updated 2026-10-18)
Plan header
Field | What to write | Your entry
New AE / start date | [Name and segment] / [first day]
Manager / onboarding buddy / enablement owner | [Sales manager] / [experienced AE] / [enablement lead]
Territory and accounts | [Region, segment, named accounts and any inherited open opportunities]
Quota and ramp schedule | [Full annual quota] / [quota relief by month, if any]
Definition of "ramped" | [e.g. the first quarter at or above an agreed share of full quota, on mostly self-sourced pipeline]
Certifications required to sell alone | [e.g. discovery role-play, tailored demo, pricing and objection role-play]
Review dates | [Day 30] / [day 60] / [day 90] / [monthly until ramped]
30-60-90 day plan
Phase | Milestone | Owner | Due | Done when | Status
1. Learn (days 1-30) | Systems and access ready | RevOps | Day 1 | Logs into every tool and records a test activity in the CRM | Not started
1. Learn (days 1-30) | ICP, buying committee and why customers buy | Manager, product marketing | Day 10 | Explains the ICP, the typical buying group and the top three reasons customers buy, in their own words | Not started
1. Learn (days 1-30) | Product and standard demo | Sales engineer | Day 15 | Gives the standard demo to the manager, covering the core workflows | Not started
1. Learn (days 1-30) | Sales process and qualification | Manager | Day 15 | Explains each stage's entry and exit criteria and the qualification framework the team uses | Not started
1. Learn (days 1-30) | Shadow live calls | Onboarding buddy | Day 20 | Shadows [x] discovery, demo and negotiation calls and notes what top AEs do | Not started
1. Learn (days 1-30) | Competitors and objections | Product marketing | Day 25 | Answers the main competitors' objections using the battlecards | Not started
1. Learn (days 1-30) | Meet cross-functional partners | Manager | Day 30 | Knows who to ask about security reviews, pricing approvals, contracts and handoff to customer success | Not started
2. Practice (days 31-60) | Discovery certification | Manager, enablement | Day 40 | Scores at the team bar on the discovery call scorecard in role-play | Not started
2. Practice (days 31-60) | Demo certification | Sales engineer, manager | Day 45 | Delivers a demo tailored to a discovery brief and passes the demo scorecard | Not started
2. Practice (days 31-60) | Pricing and objection handling | Manager, deal desk | Day 50 | Handles pricing and competitor objections in role-play within discount guardrails | Not started
2. Practice (days 31-60) | Territory and account plan | Manager | Day 50 | Top [x] target accounts prioritized, each with an account plan the manager has reviewed | Not started
2. Practice (days 31-60) | First live discovery calls | AE, manager | Day 60 | Runs [x] live discovery calls; the manager scores at least two | Not started
2. Practice (days 31-60) | Pipeline build | AE, SDR partner | Day 60 | Pipeline reaches [x] of the day-90 target, self-sourced plus SDR-booked | Not started
3. Sell (days 61-90) | Own deals end to end | AE | Day 75 | Owns opportunities from discovery to proposal and forecasts each one in the weekly call | Not started
3. Sell (days 61-90) | Mutual action plan on a late-stage deal | AE, buyer champion | Day 80 | At least one opportunity has a mutual action plan the buyer has agreed | Not started
3. Sell (days 61-90) | First closed-won deal | AE | Day 90 | First deal closed-won, or a late-stage deal with a buyer-confirmed signature date | Not started
3. Sell (days 61-90) | Day-90 review | Manager, AE | Day 90 | Milestones, scorecards and pipeline reviewed; ramp plan to full quota agreed | Not started
4. Ramp (day 91 onward) | Monthly ramp checkpoint | Manager | Monthly | Pipeline coverage, stage conversion and scorecard trend reviewed against the team | Not started
4. Ramp (day 91 onward) | Fully ramped | Manager | [Target month] | Meets the definition of "ramped" in the header | Not started
Sales onboarding checklist (access and admin)
Item | Owner | Due | Done
Laptop, email, calendar and single sign-on | IT | Before day 1 | [ ]
CRM, call recording, sales engagement and content library logins | RevOps | Before day 1 | [ ]
Onboarding buddy assigned and first meeting booked | Manager | Before day 1 | [ ]
First two weeks of sessions and shadow calls on the calendar | Enablement | Before day 1 | [ ]
Territory, account list and any inherited opportunities shared | Manager | Week 1 | [ ]
Compensation plan and quota letter explained and signed | Manager, finance | Week 1 | [ ]
Weekly one-to-one and call review slot booked | Manager | Week 1 | [ ]
Messaging framework, pitch deck and customer stories shared | Product marketing | Week 1 | [ ]
Battlecards for the main competitors shared | Product marketing | Week 2 | [ ]
Introductions to sales engineering, SDRs, customer success and partners | Manager | Week 2 | [ ]
Pricing, discount approval and deal desk process explained | Deal desk | Week 3 | [ ]
Security review, legal and procurement process explained | Sales engineer, legal | Week 4 | [ ]
Certification role-plays scheduled | Enablement | Week 4 | [ ]

## Example (fictional)
Revspire ¦ Sales onboarding plan template
Example: fictional company. Ferncastle Analytics hired Hannah Mercer, an experienced AE from a payroll software company, to sell revenue-forecasting software to mid-market logistics companies. Sales manager Rachel Imbert owns the plan, Sam Whitley is her onboarding buddy and Ivy Chen leads enablement.
Free template from https://www.revspire.io/resources/templates/sales-onboarding-plan-template (last updated 2026-10-18)
Plan header
Field | Example entry
New AE / start date | Hannah Mercer, mid-market AE / first Monday of the quarter
Manager / buddy / enablement | Rachel Imbert / Sam Whitley / Ivy Chen
Territory and accounts | Mid-market logistics, US Midwest; two inherited open opportunities
Ramp schedule | No quota in month one, then a reduced quota until month six
Definition of "ramped" | First full quarter at the team's ramped attainment bar, mostly on self-sourced pipeline
Certifications required | Discovery role-play, tailored demo, pricing and objection role-play
Plan status at day 75
Phase | Milestone | Owner | Due | Done when | Status
1. Learn | ICP, buying committee and why customers buy | Rachel Imbert | Day 10 | Explains the ICP and buying group in her own words | Done
1. Learn | Product and standard demo | Priya Nair, Solutions Engineer | Day 15 | Standard demo given to Rachel | Done
1. Learn | Shadow live calls | Sam Whitley | Day 20 | Shadowed six calls, including the Marlow & Finch Logistics pilot review | Done
1. Learn | Competitors and objections | Ferncastle product marketing | Day 25 | Answers Harborview Metrics objections from the battlecard | Done
2. Practice | Discovery certification | Rachel Imbert, Ivy Chen | Day 40 | Team bar on the discovery scorecard | Done on day 44 (second attempt; impact questions were the gap)
2. Practice | Demo certification | Priya Nair | Day 45 | Tailored demo passes the demo scorecard | Done
2. Practice | Pricing and objection handling | Rachel Imbert | Day 50 | Pricing role-play within guardrails | Done
2. Practice | Pipeline build | Hannah Mercer, Nadia Ferreira (SDR) | Day 60 | Pipeline at the day-60 target | Done: four opportunities, two booked by the SDR
3. Sell | Mutual action plan on a late-stage deal | Hannah Mercer | Day 80 | Buyer-agreed plan on one opportunity | In progress: inherited freight deal, champion reviewing the draft
3. Sell | First closed-won deal | Hannah Mercer | Day 90 | Closed-won or a buyer-confirmed signature date | At risk: security review not yet booked
3. Sell | Day-90 review | Rachel Imbert | Day 90 | Ramp plan to full quota agreed | Booked
Day-75 review notes
Finding | Action
First closed-won depends on a security review nobody has booked | Hannah asks the champion for the security contact this week; Priya Nair sends the security pack.
Discovery certification took two attempts | Rachel scores two more of Hannah's live discovery calls on impact questions before day 90.
Pipeline is healthy but half SDR-sourced | Add a self-sourcing target to the ramp plan agreed at day 90.
Example: fictional company. Ferncastle Analytics, Harborview Metrics, Marlow & Finch Logistics and every person named in this example are invented for illustration. Any resemblance to real companies or people is coincidental.

## How to use
Revspire ¦ Sales onboarding plan template
A sales onboarding plan template is a 30-60-90 day schedule for a new account executive: what they learn in the first 30 days, what they practice and certify by day 60, and the pipeline and first closed-won deal they work toward by day 90, with an owner and exit criteria for each milestone. Copy it free below.
Free template from https://www.revspire.io/resources/templates/sales-onboarding-plan-template (last updated 2026-10-18)
1. Define "ramped" before day one | Agree with sales leadership what full productivity means for this role, which certifications let an AE sell alone and how quota relief works. Put all three in the header so the plan has a finish line.
2. Have the first two weeks ready | Access, accounts, a buddy and a calendar of sessions and shadow calls should exist before the AE arrives. Use the checklist block so nothing depends on someone remembering.
3. Give each phase one job | Days 1-30 are for learning, days 31-60 for practice and certification while real deals start, days 61-90 for selling. Mixing them overloads week one and leaves the last month empty.
4. Gate solo selling on certification | Require the discovery, demo and pricing role-plays before an AE runs those calls alone. Score them with the same call scorecard managers use on live calls so the bar is consistent.
5. Put real deals in the plan early | Inherited opportunities, shadowing on live deals and pipeline targets from day 31 give the AE something real to apply training to, and a realistic shot at a first closed-won.
6. Review at 30, 60 and 90, then monthly | Hold a written review at each checkpoint against the exit criteria, and keep monthly ramp checkpoints until the AE meets the definition of ramped. Track time to each milestone by cohort.
Common mistakes
A product firehose in week one | Days of feature training before the AE understands the buyer leave little that sticks. Start with the ICP, the buying committee and why customers buy.
Ending onboarding at day 90 | Ramp usually runs past the 90-day program. Without monthly checkpoints, a slow ramp is noticed only when the quarter is missed.
Milestones without exit criteria | "Product training" can be marked done after one session. "Gives the standard demo to the manager" cannot. Write what done looks like.
Treating experienced hires as finished | A strong AE from another company still needs your buyers, product, process and competitors. Shorten the plan for them, but keep the certifications.
A plan the manager never sees | If onboarding is owned only by enablement, the manager meets the new AE at day 90. The manager owns the plan and the reviews.
Reusing the SDR plan | AEs need discovery, demo, mutual action plan, negotiation and forecasting milestones. A prospecting plan with a new title leaves those out.